━━━━━━━━━━━━━━━━━━━━

COMPASSION EDUCATION

The One-Location Plan — Minimum Viable Launch

━━━━━━━━━━━━━━━━━━━━

Gentle Steps — Compassion Education

Confidential · Prepared for Dolly

May 2026

# The One-Location Plan

Start small. Start tomorrow. You don't need a national nonprofit to bring a therapy dog into a classroom — you just need one school that says yes, one dog with the right temperament, and this plan. Under $2,000. Under 30 days. No 501(c)(3) required. Just you, showing up.

## What You Need

The Absolute Minimum
  • One school— a principal who says yes. That's it. Start with the school you already know someone at.
  • One therapy animal team— a certified therapy dog + handler from Pet Partners or Alliance of Therapy Dogs. They carry their own insurance.
  • One grade level— kindergarten or 1st grade is ideal for starting. Youngest kids, biggest "wow" factor, simplest lessons.
  • One session per month— 30 minutes. That's 9 sessions across a school year. Manageable for everyone.
  • Your time— 5-8 hours/month to coordinate, facilitate, and document.

## The Model: Monthly Therapy Dog Visit

### What Each Visit Looks Like

1. Before the visit (you, 1 hour):Send reminder to teacher. Confirm with therapy dog handler. Prepare simple lesson focus for the month (e.g., "What does a dog need?", "How do we know if a dog is happy?", "What is gentle touch?")

2. The visit (30 minutes):Therapy dog + handler arrive. Children sit in circle. You facilitate simple activity or discussion. Children take turns petting/interacting with dog under handler supervision. Brief closing ("What did you notice today?")

3. After the visit (teacher, 15 minutes):Follow-up activity — drawing, dictation, or discussion. "Draw what you learned about [dog's name] today."

### Legal Structure: You Don't Need a Nonprofit

For one school, one program, you can operate as:

• Volunteer/contractor to the school— Many schools accept outside presenters. You sign their volunteer agreement and background check. The therapy dog team carries their own liability insurance through Pet Partners ($1M coverage included with registration).

• Sole proprietor— If you want to charge a fee ($50-$100/visit to cover your time), file a Colorado business registration ($0 — no requirement for sole proprietors). Get a simple business bank account.

• Under fiscal sponsorship— If you want to accept donations or apply for small grants, a fiscal sponsor lets you do this without your own 501(c)(3). Community First Foundation, 5-7% fee.

### The Therapy Dog Team: Where to Find One

| Organization | How It Works | Cost to You |
| --- | --- | --- |
| Pet Partners | Certified therapy animal teams. Handler + dog are evaluated, registered, and insured ($1M liability). Find teams at petpartners.org/volunteer | $0 — volunteers donate time |
| Alliance of Therapy Dogs | Similar to Pet Partners. Certified teams with insurance. therapydogs.com | $0 — volunteer basis |
| R.E.A.D. Program | Reading Education Assistance Dogs. Already designed for schools. Kids read aloud to dogs. therapyanimals.org/read | $0 — volunteer handlers |
| Local shelter ambassadors | Humane Colorado, Denver Animal Shelter, and others have trained ambassador animals for school visits | $0-$75 suggested donation |

The therapy dog team is almost certainly FREE. Pet Partners and Alliance of Therapy Dogs are volunteer organizations — their handlers donate their time because they love sharing their animals. Your job is finding a team in your area and building a consistent monthly relationship with them.

## Budget: The One-Location Plan

| Item | Cost | Notes |
| --- | --- | --- |
| Therapy dog team | $0 | Volunteer (Pet Partners, ATD) |
| Your background check (school requirement) | $30-$50 | One-time, required by most districts |
| Student materials (journals, certificates) | $100-$200 | Simple booklets, completion certificates |
| Printing (parent permission forms, lesson guides) | $25-$50 | Or use school copier |
| Small thank-you for therapy dog handler | $50-$100 | Gift card, treats for the dog, appreciation gesture |
| Simple liability insurance (optional if working as school volunteer) | $0-$300 | May not be needed if school covers you as approved volunteer |
| Documentation (photos, assessment copies) | $0-$50 | Phone photos are fine. Use free Google Forms for surveys. |
| TOTAL | $205–$750 |  |

▌ Reality Check
You can do this for under $750. If you're operating as a school volunteer and the therapy team is volunteering, your actual out-of-pocket is closer to $200. The school provides the space, the therapy org provides the insurance, and you provide the facilitation and curriculum.

## 30-Day Launch Timeline

| Day | Action |
| --- | --- |
| Day 1-3 | Call the principal of a school you know. Say: "I have an idea for a monthly therapy dog visit program for kindergarten. It's free, insured, and research-backed. Can I buy you coffee and explain?" |
| Day 4-7 | Meet with principal. Bring: 1-page summary, 2 research citations, Pet Partners info (shows it's insured/certified). Ask: "Can we try 3 visits this semester as a pilot?" |
| Day 7-10 | Find a therapy dog team. Go to petpartners.org → Find a Handler. Contact local teams. Explain the school program. Ask: "Would you be willing to visit once a month?" |
| Day 10-14 | Complete school volunteer requirements (background check, volunteer form). Coordinate first visit date with teacher and handler. |
| Day 14-20 | Write 3 simple lesson plans (30 min each). Create parent permission form. Print student journals. Brief the teacher on format. |
| Day 21-25 | Send parent permission forms home. Collect returned forms. Confirm all logistics for first visit. |
| Day 25-30 | FIRST VISIT. Therapy dog enters classroom. Children sit in circle. Magic happens. Document with photos. Celebrate. |

## When to Scale Up

Run the one-location model for one semester (4-5 visits). Then ask yourself:

Scale Signals — Move to Full Model When:
  • The teacher asks "Can we do this more often?" (demand signal)
  • Other teachers or schools hear about it and ask to participate (organic growth)
  • You have photos, quotes, and at least anecdotal evidence of impact (proof)
  • You have energy and desire to make this bigger (personal readiness)
  • The principal says "I'd love to do this across more classrooms" (institutional buy-in)

When 3+ of these signals fire, go back to the Full How-to-Start Guideand begin the 16-week process. You'll be starting from a position of strength — with proof, photos, teacher testimonials, and a principal who's already on board. That's enormously more powerful than starting cold.

The one-location plan is not a lesser version. It IS the strategy for the first semester. Prove it works in one classroom, document the evidence, then use that proof to unlock everything else — grants, districts, partnerships, media. One classroom of kindergartners with one therapy dog is the seed. Everything else grows from that.